## 18 completed shelters
Details of 18 Completed Shelters
Sl. No. | Name of the ULB | Name and Address with land mark of the Shelter | Sanctioned Category | Type of Shelter | Capacity of Shelters | Project Sanction Date | Approved cost (in Lakhs) | NULM share (in lakhs) | Total Amount released from State Mission for establishing /building the Shelter | O&M amount released from State Mission | present status of the shelter as on Aug. 2020 | Linkage with educational institutions | staff details | Facilitates available in the shelter
|  |  | [New/Ref./ O&M] | [Gen/Men/ Women/ Spl.]
1 | Thiruvananthapuram | Sayahnam Old Age home,kallaimugam | Refurbishment | General | 42 | 14.01.2016 | 28.07 | 28.07 | 2807500 | 2040000 | functional with 39 inmates | University College , TVM | Manager , 6 care givers , | Food, medical facility, recreation, free food, clothing, legal aid,
2 | Thiruvananthapuram | Sakshalkaram, Kalladimugham | refurbishment | Special ( Destitute Rehabilitation) | 62 | 14.01.2016 | 33.81 | 33.81 | 3381500 | 2040000 | functional with 41 inmates | University College , TVM | manager , 6 care givers , | Food, medical facility, recreation, clothing, legal aid,
3 | Thiruvananthapuram | Karimadam Colony flat, Manacaud | New Construction | Special ( family) | 72 families | 2016 | 713 | 713 | 68923000 |  | functional 72 families | flats individual families occupies this
4 | Kollam | Mundakkal Agathi Mandiram | Refurbishment | General | 135 | 04.07.2015 | 51.9 | 51.9 | 3160000 | 360000 | Functional with 111 inmates | SN College Kollam | Manager, 3 care givers, 10 staff including cook | food, medical facility, social security measures, legal aid,
5 | Kollam | Karicode Mahila Mandiram | Refurbishment | Women | 50 | 25/09/2015 & 29/10/2015 | 54.3 | 54.3 | 1933676 | 600000 | Functional with 28 inmates | SN College Kollam | manager, 3 care givers 2 support staff | food, medical facility, social security measures, legal aid,
6 | S Paravoor | Old age Home | Refurbishment | General | 50 | 28.03.2017 | 50 | 50 | 40,00,000 | 0 | completed | Work completed except the ramp. Not started accommodating people
7 | Alappuzha | Santhimandiram valiyakulam ward m)appuzha | New | Special | 75 | 2016-02-03 | 125 | 125 | 11500000 | 300000 | functional with 29 inmates | St. Joseph College , Aleppy | manager (i/c) 3 care givers | food, entertainment, saksharatha class, medical facility, linkage pension schemes
8 | Kottayam | Near Collectorate, Muttambalam, Kottayam-686002 | Refurbishment | General | 120 | 22.02.2016 | 50 | 50 | 5000000 | 1500000 | functional with 50 inmates | Baselleous College , Kottayam | Manager, 3 care givers | food, recreation, medical facility, monthly medical camps conducted by NHM
9 | Kottayam | Near Collectorate, Muttambalam, Kottayam-686002 | New | General | 60 | 29.03.2016 | 125 | 125 | 10000000 | 0 | functional with 32 inmates | mount carmel school, kottayam | same team of muttambalam is managing for the time being | food, recreation, medical facility, monthly medical camps conducted by NHM
10 | Kochi | Good hope | Ref | Gen | 50 | 2016-02-03 | 47.5 | 47.5 | 4750000 |  | functional with 50 inmates | Cochin College | manager & 3 care taker | food, medical facility, recreation room,
Near ins dhronacharya fort kochi
11 | Kochi | Govt old age home, Thevara near Govt Vhss | Ref | Gen | 50 | 2016-02-03 | 50 | 50 | 500000 |  | functional with 48 inmates | SH College , Thevara | manager & 8 staff | food, medical facility, social security, legal aid,
12 | Kochi | Palluruthy Relief Settlement-near Kochi Municipal Corporation zonal office- | Ref | Gen | 190 | 2015-04-07 | 50 | 50 | 500000 | 600000 | functional with 190 inmates | Aquines College Eddakochi | manager, cook, doctor(part time)10 more staff , | food, medicine, entertainment, social security measures, legal aid.
13 | Kochi | Shanthibhavan, | Ref | Women | 50 | 2016-02-03 | 45.1 | 45.1 | 4510000 |  | functional with 46 inmates | St.Theresas, Ernakulam | manager 3 care givers | Food, medical fcility, recreation facility, The inmates are trained to make floor mats and mask , cloth bags etc.
Near KSRTC bus stand , Gandhinagar, Ernakulam,
14 | Kochi | Sneha bhavan annex, near ksrtc bus stand ,Ernakulam | Ref | Men | 50 | 2016-02-03 | 27.6 | 27.6 | 3260000 |  | functional 42 inmates | St. Alberts college | manager and 2 staff | food, medical facility, legal aid.
15 | Kochi | Mahila vikalanga mandiram, thevara, near old age home, thevara ferry | Ref | women | 75 | 29/09/2018 | 44 | 44 | 1760000 |  | functional 38 inmates | S.H College Thevara | manager, 3 care givers | Food, medical facility , recreation facility, the inmates are trained to make decorative candles, cloth bags, door mats
16 | Thrissur | Govt Old age Home, Ramavarma Puram, Thrissur | Refurbishment | General | 125 | 30/03/2017 | 47.65 | 47.65 | 4263518 | 0 | functional with 76 inmates | St. Mary College | manager, 2 care takers , 2 cook, contract staff -15(multy purpose) | food, medical facility, social security measures, legal aid, link with pension scheme
17 | Thrissur | Snehaveedu, Ramavarma Puram, Thrissur | Refurbishment | General | 100 | 27/01/2016 | 43.25 | 43.25 | 4325150 | 120000 | functional with 47 inmates | Christ College , irringalakkuda | manager, 3 care takers,2 nurses, | food, medical facility, social security measures, legal aid,
18 | Kannur | ABHAYA Nikethan , Thottada, Kannur | Refurbishment | Both Men Women | 50 | 2017-06-02 | 50 | 50 | 4000000 | 0 | Functional with 30 inmates | SN College Kannur | manager, matron, cook, cleaning worker, watchman. | food, medical facility, social security, legal aid,
[7 empty] | 1636 | 1636 | 1345 | 75

## 21 shelters under different sta
Plan of action of 21 Shelters in different stages of implementation
Sl. No. | Name of the ULB | Name and Address with land mark of the Shelter | Sanctioned Category | Type of Shelter | Capacity of Shelters | Project Sanction Date | Aproved cost (in Lakhs) | NULM share (in lakhs) | Total Amount released from State Mission for establishing /building the Sheleter | present status of the shelter as on 30 July 2020 | Plan of action
|  |  | [New/Ref./ O&M] | [Gen/Men/ Women/ Spl.]
1 | Thiruvananthapuram | Bystander’s Shelter, SAT Hospital, Medical College | Refurbishment | Men | 60 | 29.09.2018 | 50 | 44 | 17,60,000 | 90% work completed | Will be made functional by september last week
2 | Thiruvananthapuram | Bystander’s Shelter, SAT Hospital, Medical College | New Construction | General | 86 | 29.09.2018 | 337 | 268.5 | 1,07,40,000 | Construction started | construction work will be completed by June 2021 | will be made functional by August 2021
3 | Nedumangad | Old age Home | Refurbishment | General | 25 | 29.09.201 | 50 | 50 | 2000000 | 95 % work completed. 2nd installment requested | Will be made functional by October first week |  |  | 296928000
4 | Attingal | Bystander’s Shelter, at THQ Hospital | New | Hospital Bystanders | 50 | 29.09.2018 | 230 | 170 | 6800000 | TS Pending | TS will be obtaine by october 2020 and te construction completed by may 2021
5 | Kollam | Ashraya gramam old age home | New Construction | General | 70 | 28.03.2017 | 340 | 340 | 29692800 | 98% completed. | made functional by september last week
6 | Punaloor | Construction of Thanal old age homel 3 | New | General | 78 | 28.03.2017 | 345 | 345 | 13830400 | 1st Floor Complted | will be made functional by Jan 2021
7 | Haripad | Taluk Head Quarter Hospital, Haripad | New | Hospital Bystanders | 50 | 29.09.2018 | 120 | 104.64 | 4185600 | TS received butwork not commenced as they are waiting for the samction from the health department
8 | Pathanamthitta | “Koodu” Shelter, Kallarakadavu, Pathanamthitta | New | Gen | 50 | 29.09.2018 | 320 | 190.6 | 7624000 | TS Pending | TS will be obtaine by october 2020 and te construction completed by July 2021 | Construction will be completd by July 2021 | will be made functional by August 2021
9 | Kattappana | Thanal, Kattappana | New | General | 50 | 29.09.2018 | 315 | 233 | 9320000 | TS Pending , File is pending with SE office. They are waiting for the report for commencing the work | TS will be obtained by October 2020 | Construction will be completed by April 2022 | Will be made functional by May 2022
10 | Piravom | Ashrayabhavan Destitute home for men and women | New | General | 100 | 28.03.2017 | 300 |  | 12000000 | ground floor brik work comleted | December 2020 the cnstruction will be completed | Made functional by March 2021
11 | North Paravoor | Paravur Abhayakendram | New | women | 50 | 29/09/2018 | 141.5 | 125 | 5000000 | Ground floor column work completed | December 2020 the cnstruction will be completed | Made functional by March 2021
12 | Guruvayoor | Stay Home for Women | New | women | 64 | 29/09/2018 | 375 | 242.75 | 9710000 | ground clearing | construction will be completed in september 2021 | made functional by October 2021
13 | Palakkad | Thottupalam Shelter home, Palakkad | New | General | 116 | 08.03.2019 | 250 | 250 | 0 | TS obtained , work order will be given | G + 1 construction will be completed by september 2021 | made functional by October 2021
14 | Shornur | Abhaya Kendram, Nedungottur, Shornur | New | General | 50 | 08.03.2019 | 201.3 | 181.4 | 7256000 | Work order given to FPRL - prefab | construction will be completed by January 2021 | Made functional by March 2021
15 | Malappuram | Karunya Bhavan, Nechikkutty, Malappuram | New | General | 55 | 29.09.2018 | 251 | 173 | 6920000 | T.S Pending, T.S request rejected from S.E office due to the absence of ULB share. Now that issue solved. | TS will be obtained by October 2020 | Construction will be completd by July 2021 | Made functional by Augustn 2021
16 | Perinthalmanna | Vayojana Mithram Rehabilitation Centre | New | General | 111 | 29.09.2018 | 337 | 250 | 10000000 | Construction completed | made functional by October 2020
17 | Kalpetta | Thanaloram Shelter Home, Nr. PHC, Munderi | New | General | 55 | 2017-06-02 | 150 | 150 | 6000000 | Up to roof top of ground floor completed. | Construction will be completed in March 2021 | will be made functional by April 2021
18 | Payyannur | Taluk Head Quarter Hospital, Payyannur | New | Hospital Bystanders | 54 | 29.09.2018 | 162 | 127 | 5080000 | TS Pending, Application rejected from SE office Kozhikode, file forwarded again to kannur Govt Eng colllage for structural scrutiny. | TS will be obtained by October 2020 | Construction will be completed by August 2021 | Made functional by Sep.2021
19 | Kanhangad | Shelter home, Melankode, Kanhangad | New | Gen | 75 | 29.09.2018 | 311.76 | 266.76 | 11000000 | TS pending | TS will be obtained by Novmber 2020 | Construction will be completed by December 2021 | Made functional by Jan 2022 | 6702
20 | Kozhikode | Shelter home for destitutes | New Construction | gen | 100 | 28.7.2020 | 250 | 250 |  | Applied for TS | obtaining TS by end of september 2020 | construction will be completd by July 2021 | made functional by Augustn 2021 | 5647
21 | Kottayam | Shelter for | New Construction | Women | 300 | 17.8.2020 | 250 | 250 | 0 | Applied for TS | obtaining TS by end of september 2020 | construction work will be completed by june 2022 | made functional by Augustn 2022
[7 empty] | 5065 | 4011 | 1464