## G-1
Goal -1:- Setting up of 100 urban vegetable kiosks in all districts
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 (identification of locations) | Cumulative achievement as on 5th Oct. 2020(identification of locations ) | Cumulative achievement as on 12th Oct. 20209(identification of locations) | Cumulative achievement as on 19th Oct. 2020 (identification of locations) | Cumulative achievement as on 26th Oct. 2020(Identification of locations) | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020(identification of locations) | cumulative achievement as on 16th Nov. 2020(identification of locations) | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
2 | Kollam | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
3 | Pathanamthitta | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
4 | Alappuzha | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
4 | Kottayam | 7 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 7
6 | Idukki | 7 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7 | Ernakulam | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
8 | Trissur | 8 |  | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10
9 | Palakkad | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
10 | Malappuram | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8
11 | Kozhikode | 7 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7
12 | Waynad | 7 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4
13 | Kannur | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
14 | Kasaragod | 7 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
[11 empty] | 92 | 92 | 92

## G-2
Goal -2:- CIG (Common Interest groups): formation of 200 new CIGs in dairy sector will be completed .
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 18 | 0 | Fund allocated | 0 | 0 | 0 | 21 | 21 | 21 | 21 | 21 | 21
2 | Kollam | 15 | 0 | Fund allocated | 0 | 1 | 1 | 1 | 1 | 15 | 15 | 15 | 15
3 | Pathanamthitta | 13 | 0 | Fund allocated | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 16
4 | Alappuzha | 18 | 0 | Fund allocated | 0 | 1 | 1 | 7 | 7 | 8 | 12 | 16 | 18
4 | Kottayam | 15 | 0 | Fund allocated | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 12 | 13
6 | Idukki | 10 | 0 | Fund allocated | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5
7 | Ernakulam | 17 | 0 | Fund allocated | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19
8 | Trissur | 17 | 0 | Fund allocated | 0 | 0 | 0 | 0 | 0 | 24 | 30 | 30 | 30
9 | Palakkad | 20 | 0 | Fund allocated | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 22 | 22
10 | Malappuram | 7 | 0 | Fund allocated | 0 | 0 | 0 | 6 | 6 | 7 | 7 | 7 | 7
11 | Kozhikode | 9 | 0 | Fund allocated | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 8
12 | Waynad | 23 | 0 | Fund allocated | 0 | 0 | 0 | 9 | 9 | 12 | 15 | 17 | 23
13 | Kannur | 15 | 0 | Fund allocated | 0 | 0 | 0 | 3 | 3 | 3 | 7 | 15 | 15
14 | Kasaragod | 3 | 0 | Fund allocated | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3
|  | 200 |  |  | 0 | 5 | 5 | 65 | 65 | 129 | 168 | 198 | 215

## G-3
Goal -3:- 10,00,000 Kudumbashree members will be enrolled in the new Insurance scheme
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
2 | Kollam | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
3 | Pathanamthitta | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
4 | Alappuzha | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
4 | Kottayam | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
6 | Idukki | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
7 | Ernakulam | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
8 | Trissur | 100000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
9 | Palakkad | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
10 | Malappuram | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
11 | Kozhikode | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
12 | Waynad | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
13 | Kannur | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
14 | Kasaragod | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Circular given to District | Training given to Bima Mitra | Enrollment started
1000000

## G-4
Goal -4:- 5000 Micro Enterprices (ME) units will be insured
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Kollam | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Pathanamthitta | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Alappuzha | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Kottayam | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Idukki | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Ernakulam | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Trissur | 400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Palakkad | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Malappuram | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Kozhikode | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Waynad | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Kannur | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Kasaragod | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000

## G-5
Goal -5:- 20,000 individuals involving in Micro Enterprices (ME) activities ( members of Harithakarma sena and constuction team) will be insured
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Kollam | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Pathanamthitta | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Alappuzha | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Kottayam | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Idukki | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Ernakulam | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Trissur | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Palakkad | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Malappuram | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Kozhikode | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Waynad | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Kannur | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Kasaragod | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20000

## G-6
Goal -6:- Establishing 100 E-SEVA kiosks
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Kollam | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Pathanamthitta | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Alappuzha | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Kottayam | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Idukki | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Ernakulam | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Trissur | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Palakkad | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Malappuram | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Kozhikode | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Waynad | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Kannur | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Kasaragod | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100

## G-7
Goal -7:- ITI Canteen-Canteen units will be identified-(100 canteens will be opened)
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 (identification of spots finalised ) | Cumulative achievement as on 5th Oct. 2020(identification of spots) | Cumulative achievement as on 12th Oct. 2020(identification of spots) | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
2 | Kollam | 9 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
3 | Pathanamthitta | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
4 | Alappuzha | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
4 | Kottayam | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
6 | Idukki | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
7 | Ernakulam | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
8 | Trissur | 7 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
9 | Palakkad | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
10 | Malappuram | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
11 | Kozhikode | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
12 | Waynad | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
13 | Kannur | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
14 | Kasaragod | 9 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9

## G-8
Goal -8:- Marketing Outlet - Establish (100 Marketing Outlets)
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 7 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued |  | Proceedings issued | Proceedings issued | Proceedings issued | Agency not selected.Proposls received from agencies
2 | Kollam | 6 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 4 outlets |  | Proceedings issued for starting 4 outlets | Proceedings issued for starting 4 outlets | Proceedings issued for starting 4 outlets
3 | Pathanamthitta | 7 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | DPR submission pending |  | DPR submission pending | DPR submission pending | DPR submission pending
4 | Alappuzha | 11 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for Starting 4 outlets |  | Proceedings issued for Starting 4 outlets | Proceedings issued for Starting 4 outlets | Proceedings issued for Starting 4 outlets | Agency selected is SIDCO.work order not issued
4 | Kottayam | 3 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 1 outlet |  | Proceedings issued for starting 1 outlet | Proceedings issued for starting 1 outlet | Proceedings issued for starting 1 outlet
6 | Idukki | 3 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 2 outlets |  | Proceedings issued for starting 2 outlets | Proceedings issued for starting 2 outlets | Proceedings issued for starting 2 outlets
7 | Ernakulam | 12 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 9 outlets |  | Proceedings issued for starting 9 outlets | Proceedings issued for starting 9 outlets | Proceedings issued for starting 9 outlets
8 | Trissur | 12 |  | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 8 outlets |  | Work Order Issued | Work Order Issued | Work order given to KSIE | Agency selected is KSIE.Work order not issued.
9 | Palakkad | 1 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued |  | Proceedings issued | Proceedings issued | Proceedings issued | Agency selected is ARTCO.Work order will issue in December
10 | Malappuram | 8 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 5 outlets |  | Proceedings issued for starting 5 outlets | Proceedings issued for starting 5 outlets | Proceedings issued for starting 5 outlets | Work order Issued. agency selected KSIE
11 | Kozhikode | 10 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for 9 outlets |  | Proceedings issued for 9 outlets | Proceedings issued for 9 outlets | Work order for 8 outlets issued | Work order issued for 8 outlets.KSIE is selected for the work
12 | Waynad | 3 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | DPR submission pending |  | DPR submission pending | DPR submission pending | DPR submission pending
13 | Kannur | 5 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 4 outlets |  | Proceedings issued for starting 4 outlets | Proceedings issued for starting 4 outlets | word order Issuing process started | Work order not issued.Proposals received from agencies
14 | Kasaragod | 12 | 0 | DPR preparation on going | DPR preparation on going | DPR appraisal committe on 16th | DPR appraisal committee held | Proceedings issued for starting 8 outlet |  | Proceedings issued for starting 8 outlet | Proceedings issued for starting 8 outlet | Proceedings issued for starting 8 outlet | Agency selected for the work is Nirmmithi kendra.Work order not issued.

## G-9
Goal -9:- Pink Cafe - will start 10 Pink Café
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 1 | 0 | Pink cafe work in progress( KSRTC Bus)in association with KSRTC | Pink cafe work in progress( KSRTC Bus)in association with KSRTC | Pink cafe work in progress( KSRTC Bus)in association with KSRTC | Pink cafe work in progress( KSRTC Bus)in association with KSRTC | Inaguration on November first week | Pink Cafe Inaugurated in Kizhakkekotta |  |  | Pink Cafe Inaugurated in Kizhakkekotta | Pink Cafe Inaugurated in Kizhakkekotta
2 | Kollam | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
3 | Pathanamthitta | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
4 | Alappuzha | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
4 | Kottayam | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
6 | Idukki | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
7 | Ernakulam | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
8 | Trissur | 1 |  | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
9 | Palakkad | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
10 | Malappuram | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
11 | Kozhikode | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
12 | Waynad | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
13 | Kannur | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification
14 | Kasaragod | 1 | 0 | 0 | 0 | 0 | 0 | location and beneficiary identification | location and beneficiary identification |  |  | location and beneficiary identification | location and beneficiary identification

## G-10
Goal -10:- Community Enterprises Fund - Disburse 6000 loans
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 635 | 29 | 29 | 29 | 156 | 156 | 156 | 156 |  | 385 | 385 | 407
2 | Kollam | 422 | 74 | 74 | 74 | 142 | 142 | 167 | 167 |  | 167 | 196 | 196
3 | Pathanamthitta | 327 | 125 | 125 | 125 | 226 | 226 | 226 | 226 |  | 454 | 454 | 454
4 | Alappuzha | 474 | 214 | 214 | 214 | 345 | 345 | 345 | 345 |  | 391 | 391 | 401
4 | Kottayam | 443 | 147 | 147 | 147 | 180 | 180 | 180 | 180 |  | 254 | 254 | 270
6 | Idukki | 188 | 103 | 103 | 103 | 78 | 78 | 78 | 78 |  | 139 | 139 | 139
7 | Ernakulam | 778 | 48 | 144 | 144 | 312 | 312 | 312 | 312 |  | 485 | 485 | 522
8 | Trissur | 866 | 335 | 335 | 335 | 511 | 511 | 511 | 511 |  | 614 | 614 | 635
9 | Palakkad | 287 | 5 | 5 | 5 | 10 | 10 | 18 | 18 |  | 37 | 44 | 50
10 | Malappuram | 358 | 0 | 0 | 0 | 155 | 155 | 155 | 155 |  | 197 | 197 | 205
11 | Kozhikode | 540 | 60 | 60 | 60 | 179 | 179 | 179 | 179 |  | 230 | 230 | 241
12 | Waynad | 236 | 58 | 58 | 58 | 68 | 68 | 68 | 68 |  | 138 | 138 | 138
13 | Kannur | 256 | 36 | 36 | 36 | 63 | 63 | 63 | 63 |  | 78 | 97 | 145
14 | Kasaragod | 190 | 0 | 0 | 0 | 0 | 0 | 12 | 12 |  | 26 | 26 | 37
[8 empty] | 2470 | 2470 |  | 3595 | 3624 | 3840

## G-11
Goal -11:- BUDS Livelihood: Will start livelihood programmes at 150 buds institutions.
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 14 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 | Guidelines issued | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week | training will start by next week
2 | Kollam | 14 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
3 | Pathanamthitta | 1 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
4 | Alappuzha | 9 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
4 | Kottayam | 1 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
6 | Idukki | 2 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
7 | Ernakulam | 24 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
8 | Trissur | 8 |  | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
9 | Palakkad | 8 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
10 | Malappuram | 21 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
11 | Kozhikode | 18 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
12 | Waynad | 4 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
13 | Kannur | 20 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
14 | Kasaragod | 6 | 0 | DPR verification | Fund Allocated | DMT presentation Planned | DMT presentation planned on 20th Oct.2020 | DMT presentation completed. Trainingswill start on 1st of November 2020 |  | Guidelines issued | File put up for DPR approval. | Approved the proposals. Will start the training by next Week
150

## G-12
Goal -12:- 20000 street vendors will be supported with Pradhan Mantri Street vendor's AtmaNirbhar Nidhi (PMSVANIdhi ) , (Rs,10000/- as working capital loan for 20000 street vendors)
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 1750 | 154 | 193 | 265 | 308 | 355 | 426 |  | 494 | 532 | 580 | 645
2 | Kollam | 550 | 44 | 65 | 75 | 82 | 88 | 89 |  | 109 | 113 | 131 | 151
3 | Pathanamthitta | 300 | 39 | 82 | 86 | 88 | 95 | 96 |  | 111 | 118 | 127 | 158
4 | Alappuzha | 550 | 66 | 71 | 89 | 99 | 109 | 123 |  | 136 | 146 | 155 | 178
4 | Kottayam | 400 | 89 | 152 | 179 | 211 | 238 | 273 |  | 335 | 344 | 337 | 418
6 | Idukki | 180 | 43 | 86 | 97 | 107 | 111 | 117 |  | 126 | 135 | 141 | 154
7 | Ernakulam | 1650 | 207 | 303 | 347 | 367 | 447 | 467 |  | 513 | 533 | 637 | 736
8 | Trissur | 950 | 264 | 328 | 354 | 407 | 461 | 498 |  | 542 | 545 | 620 | 688
9 | Palakkad | 700 | 162 | 270 | 277 | 312 | 328 | 332 |  | 377 | 386 | 416 | 520
10 | Malappuram | 650 | 85 | 110 | 128 | 154 | 171 | 177 |  | 198 | 205 | 234 | 298
11 | Kozhikode | 1350 | 220 | 300 | 309 | 340 | 362 | 369 |  | 406 | 421 | 471 | 526
12 | Waynad | 250 | 27 | 32 | 37 | 38 | 51 | 55 |  | 65 | 67 | 75 | 88
13 | Kannur | 550 | 133 | 170 | 178 | 194 | 210 | 221 |  | 242 | 256 | 284 | 345
14 | Kasaragod | 170 | 53 | 62 | 62 | 65 | 76 | 77 |  | 91 | 91 | 96 | 102
|  |  | 1586 | 2224 | 2483 | 2772 | 3102 | 3321 |  | 3745 | 3892 | 4339 | 5008

## G-13
Goal -13:- Sanction of loan under Credit Linked Subsidy Scheme (CLSS) to 1000 beneficiaries
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram |  | 0
2 | Kollam |  | 0
3 | Pathanamthitta |  | 0
4 | Alappuzha |  | 0
4 | Kottayam |  | 0
6 | Idukki |  | 0
7 | Ernakulam |  | 0
8 | Trissur
9 | Palakkad |  | 0
10 | Malappuram |  | 0
11 | Kozhikode |  | 0
12 | Waynad |  | 0
13 | Kannur |  | 0
14 | Kasaragod |  | 0

## G-14
Goal -14:- Issue Building Permits to all newly sanctioned houses - Goal is to issue building permit to 13, 646 beneficiaries before November 30th 2020
Sl No | Name of District | Target | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Alappuzha | 739 | 126 | 137 | 141 | 141 | 150 | 150 | 150 | 155 | 162 | 162 | 171
2 | Ernakulam | 2509 | 547 | 577 | 593 | 607 | 617 | 620 | 632 | 647 | 690 | 690 | 803
3 | Idukki | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Kannur | 792 | 447 | 465 | 472 | 495 | 520 | 540 | 540 | 545 | 545 | 575 | 654
5 | Kasaragod | 133 | 5 | 7 | 10 | 10 | 10 | 10 | 10 | 58 | 58 | 58 | 60
6 | Kollam | 1873 | 830 | 834 | 853 | 867 | 870 | 881 | 881 | 881 | 881 | 881 | 887
7 | Kottayam | 440 | 34 | 34 | 41 | 42 | 44 | 44 | 44 | 44 | 44 | 44 | 48
8 | Kozhikode | 1441 | 1062 | 1092 | 1095 | 1095 | 1095 | 1103 | 1103 | 1103 | 1103 | 1103 | 1117
9 | Malappuram | 337 | 223 | 226 | 250 | 250 | 256 | 256 | 256 | 278 | 278 | 278 | 278
10 | Palakkad | 1458 | 817 | 880 | 908 | 908 | 940 | 952 | 952 | 952 | 952 | 952 | 1092
11 | Pathanamthitta | 619 | 126 | 137 | 173 | 189 | 197 | 211 | 211 | 211 | 211 | 211 | 220
12 | Thiruvananthapuram | 1721 | 608 | 608 | 615 | 615 | 615 | 634 | 634 | 634 | 634 | 718 | 936
13 | Trissur | 1135 | 933 | 933 | 948 | 951 | 951 | 953 | 953 | 980 | 980 | 980 | 994
14 | Waynad | 166 | 47 | 47 | 51 | 61 | 75 | 87 | 87 | 87 | 87 | 87 | 127
TOTAL |  | 13646 | 5805 | 5977 | 6150 | 6231 | 6340 | 6441 | 6453 | 6575 | 6625 | 6739 | 7387

## G-15
Goal -15:- Kudubashree Sanitising Teams to execute 1000 work orders from different agencies in 100 days
Sl No | Name of District | Target (Total Work order) | Cumulative Achievement as on 21st Sept.2020 | Cumulative achievement as on 28th sept.2020 | Cumulative achievement as on 5th Oct. 2020 | Cumulative achievement as on 12th Oct. 2020 | Cumulative achievement as on 19th Oct. 2020 | Cumulative achievement as on 26th Oct. 2020 | Cumulative achievement as on 2nd Nov. 2020 | Cumulative Achievement as on 9th Nov. 2020 | cumulative achievement as on 16th Nov. 2020 | cumulative achievement as on 23rd Nov. 2020 | cumulative achievement as on 30th Nov. 2020
1 | Thiruvananthapuram | 100 | Progressing | Total number of sanitising Teams: 5 Total work orders executed : 26 Total amount earned by Teams: Rs. 142591 | Total number of sanitising Teams:5 Total work orders executed :38 Total amount earned by Teams: Rs. 266985 | Total number of sanitising Teams:5 Total work orders executed :58 Total amount earned by Teams: Rs. 374451 | Total number of sanitising Teams:5 Total work orders executed :70 Total amount earned by Teams: Rs. 471649 | Total number of sanitising Teams:5 Total work orders executed :80 Total amount earned by Teams: Rs. 555759 | Total number of sanitising Teams:5 Total work orders executed :96 Total amount earned by Teams: Rs. 604109 | Total number of sanitising Teams:5 Total work orders executed :100 Total amount earned by Teams: Rs. 611889 | Total number of sanitising Teams:5 Total work orders executed :109 Total amount earned by Teams: Rs. 641123 | Total number of sanitising Teams:5 Total work orders executed :110 Total amount earned by Teams: Rs. 642923 | Total number of sanitising Teams:5 Total work orders executed :116 Total amount earned by Teams: Rs. 676726
2 | Kollam | 65 | Progressing | Total number of sanitising Teams: 1 Total work orders executed : 11 Total amount earned by Teams: Rs. 23745 | Total number of sanitising Teams: 1 Total work orders executed : 12 Total amount earned by Teams: Rs. 24695 | Total number of sanitising Teams: 1 Total work orders executed : 24 Total amount earned by Teams: Rs. 40415 | Total number of sanitising Teams: 2 Total work orders executed : 33 Total amount earned by Teams: Rs. 65975 | Total number of sanitising Teams: 3 Total work orders executed : 46 Total amount earned by Teams: Rs. 79925 | Total number of sanitising Teams: 5 Total work orders executed : 72 Total amount earned by Teams: Rs. 104245 | Total number of sanitising Teams: 7 Total work orders executed : 101 Total amount earned by Teams: Rs. 132605 | Total number of sanitising Teams: 7 Total work orders executed : 146 Total amount earned by Teams: Rs. 176095 | Total number of sanitising Teams: 7 Total work orders executed : 169 Total amount earned by Teams: Rs. 203105 | Total number of sanitising Teams: 7 Total work orders executed : 190 Total amount earned by Teams: Rs. 224380
3 | Pathanamthitta | 60 | Progressing | Total number of sanitising Teams:2 Total work orders executed : 2 Total amount earned by Teams: Rs. 5000 | Total number of sanitising Teams:2 Total work orders executed : 3 Total amount earned by Teams: Rs. 7000 | Total number of sanitising Teams:2 Total work orders executed : 4 Total amount earned by Teams: Rs. 10000 | Total number of sanitising Teams:3 Total work orders executed : 7 Total amount earned by Teams: Rs. 19224 | Total number of sanitising Teams:3 Total work orders executed : 10 Total amount earned by Teams: Rs. 29224 | Total number of sanitising Teams:3 Total work orders executed : 10 Total amount earned by Teams: Rs. 29224 | Total number of sanitising Teams:3 Total work orders executed : 12 Total amount earned by Teams: Rs. 32724 | Total number of sanitising Teams:4 Total work orders executed : 14 Total amount earned by Teams: Rs. 39224 | Total number of sanitising Teams:4 Total work orders executed : 14 Total amount earned by Teams: Rs. 39224 | Total number of sanitising Teams:4 Total work orders executed : 15 Total amount earned by Teams: Rs. 40424
4 | Alappuzha | 100 | Progressing | Total number of sanitising Teams:15 Total work orders executed : 53 Total amount earned by Teams: Rs. 108400 | Total number of sanitising Teams:15 Total work orders executed : 53 Total amount earned by Teams: Rs. 108400 | Total number of sanitising Teams:15 Total work orders executed : 58 Total amount earned by Teams: Rs. 116280 | Total number of sanitising Teams:16 Total work orders executed : 132 Total amount earned by Teams: Rs. 281086 | Total number of sanitising Teams:16 Total work orders executed : 164 Total amount earned by Teams: Rs. 322886 | Total number of sanitising Teams:17 Total work orders executed : 214 Total amount earned by Teams: Rs. 390515 | Total number of sanitising Teams:17 Total work orders executed : 253 Total amount earned by Teams: Rs. 446765 | Total number of sanitising Teams:17 Total work orders executed : 268 Total amount earned by Teams: Rs. 460765 | Total number of sanitising Teams:18 Total work orders executed : 282 Total amount earned by Teams: Rs. 483165 | Total number of sanitising Teams:18 Total work orders executed : 298 Total amount earned by Teams: Rs. 498056
5 | Kottayam | 70 | Progressing | Total number of sanitising Teams: 5 Total work orders executed : 6 Total amount earned by Teams: Rs. 17800 | Total number of sanitising Teams: 5 Total work orders executed : 13 Total amount earned by Teams: Rs. 38850 | Total number of sanitising Teams: 5 Total work orders executed : 24 Total amount earned by Teams: Rs. 60900 | Total number of sanitising Teams: 6 Total work orders executed : 58 Total amount earned by Teams: Rs. 119770 | Total number of sanitising Teams: 9 Total work orders executed : 95 Total amount earned by Teams: Rs. 186240 | Total number of sanitising Teams: 9 Total work orders executed : 123 Total amount earned by Teams: Rs. 218040 | Total number of sanitising Teams: 9 Total work orders executed : 128 Total amount earned by Teams: Rs. 227690 | Total number of sanitising Teams: 10 Total work orders executed : 130 Total amount earned by Teams: Rs. 238690 | Total number of sanitising Teams: 10 Total work orders executed : 134 Total amount earned by Teams: Rs. 242690 | Total number of sanitising Teams: 10 Total work orders executed : 135 Total amount earned by Teams: Rs. 258290
6 | Idukki | 60 | Progressing | Total number of sanitising Teams: 4 Total work orders executed : 14 Total amount earned by Teams: Rs. 23350 | Total number of sanitising Teams: 4 Total work orders executed : 16 Total amount earned by Teams: Rs. 26500 | Total number of sanitising Teams: 4 Total work orders executed : 24 Total amount earned by Teams: Rs. 33350 | Total number of sanitising Teams: 4 Total work orders executed : 26 Total amount earned by Teams: Rs. 42300 | Total number of sanitising Teams: 4 Total work orders executed : 27 Total amount earned by Teams: Rs. 44800 | Total number of sanitising Teams: 4 Total work orders executed : 31 Total amount earned by Teams: Rs.60300 | Total number of sanitising Teams: 5 Total work orders executed : 42 Total amount earned by Teams: Rs.82540 | Total number of sanitising Teams: 5 Total work orders executed : 58 Total amount earned by Teams: Rs.95325 | Total number of sanitising Teams: 5 Total work orders executed : 67 Total amount earned by Teams: Rs.114721 | Total number of sanitising Teams: 5 Total work orders executed : 82 Total amount earned by Teams: Rs.134924
7 | Ernakulam | 80 | Progressing | Total number of sanitising Teams: 3 Total work orders executed : 21 Total amount earned by Teams: Rs. 109650 | Total number of sanitising Teams: 3 Total work orders executed : 21 Total amount earned by Teams: Rs. 109650 | Total number of sanitising Teams: 3 Total work orders executed : 37 Total amount earned by Teams: Rs. 225968 | Total number of sanitising Teams: 4 Total work orders executed : 41 Total amount earned by Teams: Rs. 240468 | Total number of sanitising Teams: 4 Total work orders executed : 46 Total amount earned by Teams: Rs. 263168 | Total number of sanitising Teams: 4 Total work orders executed : 68 Total amount earned by Teams: Rs. 311468 | Total number of sanitising Teams: 8 Total work orders executed : 85 Total amount earned by Teams: Rs. 342068 | Total number of sanitising Teams: 8 Total work orders executed : 94 Total amount earned by Teams: Rs. 380168 | Total number of sanitising Teams: 8 Total work orders executed : 98 Total amount earned by Teams: Rs. 385568 | Total number of sanitising Teams: 8 Total work orders executed : 106 Total amount earned by Teams: Rs. 393968
8 | Thrissur | 65 | Progressing | Total number of sanitising Teams: 3 Total work orders executed : 8 Total amount earned by Teams: Rs. 22000 | Total number of sanitising Teams: 3 Total work orders executed : 17 Total amount earned by Teams: Rs. 38500 | Total number of sanitising Teams: 3 Total work orders executed : 23 Total amount earned by Teams: Rs. 51000 | Total number of sanitising Teams: 3 Total work orders executed : 36 Total amount earned by Teams: Rs. 84530 | Total number of sanitising Teams: 3 Total work orders executed : 41 Total amount earned by Teams: Rs. 107660 | Total number of sanitising Teams: 3 Total work orders executed : 59 Total amount earned by Teams: Rs. 131200 | Total number of sanitising Teams: 3 Total work orders executed : 61 Total amount earned by Teams: Rs. 159045 | Total number of sanitising Teams: 3 Total work orders executed : 69 Total amount earned by Teams: Rs. 199579 | Total number of sanitising Teams: 3 Total work orders executed : 76 Total amount earned by Teams: Rs.224779 | Total number of sanitising Teams: 3 Total work orders executed : 84 Total amount earned by Teams: Rs.243299
9 | Palakkad | 65 | Progressing | Total number of sanitising Teams: 2 Total work orders executed : 1 Total amount earned by Teams: Rs. 1200 | Total number of sanitising Teams: 2 Total work orders executed : 3 Total amount earned by Teams: Rs. 4200 | Total number of sanitising Teams: 3 Total work orders executed : 7 Total amount earned by Teams: Rs. 9050 | Total number of sanitising Teams: 3 Total work orders executed : 11 Total amount earned by Teams: Rs. 17425 | Total number of sanitising Teams: 3 Total work orders executed : 13 Total amount earned by Teams: Rs. 21925 | Total number of sanitising Teams: 3 Total work orders executed : 17 Total amount earned by Teams: Rs. 30125 | Total number of sanitising Teams: 3 Total work orders executed : 22 Total amount earned by Teams: Rs. 38125 | Total number of sanitising Teams: 3 Total work orders executed : 27 Total amount earned by Teams: Rs. 46875 | Total number of sanitising Teams: 3 Total work orders executed : 30 Total amount earned by Teams: Rs. 66175 | Total number of sanitising Teams: 3 Total work orders executed : 32 Total amount earned by Teams: Rs. 75075
10 | Malappuram | 65 | Progressing | Total number of sanitising Teams:1 Total work orders executed : 0 Total amount earned by Teams: Rs. 0 | Total number of sanitising Teams:1 Total work orders executed : 0 Total amount earned by Teams: Rs.0 | Total number of sanitising Teams:1 Total work orders executed : 0 Total amount earned by Teams: Rs.0 | Total number of sanitising Teams:1 Total work orders executed : 4 Total amount earned by Teams: Rs.10000 | Total number of sanitising Teams:2 Total work orders executed : 5 Total amount earned by Teams: Rs.11000 | Total number of sanitising Teams:2 Total work orders executed : 7 Total amount earned by Teams: Rs.15700 | Total number of sanitising Teams:3 Total work orders executed : 11 Total amount earned by Teams: Rs.24030 | Total number of sanitising Teams:4 Total work orders executed : 16 Total amount earned by Teams: Rs.26730 | Total number of sanitising Teams:7 Total work orders executed : 24 Total amount earned by Teams: Rs.32430 | Total number of sanitising Teams:7 Total work orders executed : 27 Total amount earned by Teams: Rs.52580
11 | Kozhikode | 80 | Progressing | Total number of sanitising Teams: 3 Total work orders executed : 4 Total amount earned by Teams: Rs. 14500 | Total number of sanitising Teams: 3 Total work orders executed : 5 Total amount earned by Teams: Rs. 16500 | Total number of sanitising Teams: 3 Total work orders executed : 19 Total amount earned by Teams: Rs. 88500 | Total number of sanitising Teams: 4 Total work orders executed : 48 Total amount earned by Teams: Rs. 111800 | Total number of sanitising Teams: 4 Total work orders executed : 53 Total amount earned by Teams: Rs. 128100 | Total number of sanitising Teams: 5 Total work orders executed : 59 Total amount earned by Teams: Rs. 131200 | Total number of sanitising Teams: 6 Total work orders executed : 66 Total amount earned by Teams: Rs. 139600 | Total number of sanitising Teams: 6 Total work orders executed : 73 Total amount earned by Teams: Rs. 148200 | Total number of sanitising Teams: 6 Total work orders executed : 73 Total amount earned by Teams: Rs. 148200 | Total number of sanitising Teams: 6 Total work orders executed : 91 Total amount earned by Teams: Rs. 161200
12 | Wayanad | 60 | Progressing | Total number of sanitising Teams: 7 Total work orders executed : 28 Total amount earned by Teams: Rs. 73300 | Total number of sanitising Teams: 7 Total work orders executed : 28 Total amount earned by Teams: Rs. 73300 | Total number of sanitising Teams: 7 Total work orders executed : 35 Total amount earned by Teams: Rs. 80050 | Total number of sanitising Teams: 4 Total work orders executed : 42 Total amount earned by Teams: Rs. 116730 | Total number of sanitising Teams: 7 Total work orders executed : 48 Total amount earned by Teams: Rs. 121280 | Total number of sanitising Teams: 8 Total work orders executed : 56 Total amount earned by Teams: Rs. 127980 | Total number of sanitising Teams: 8 Total work orders executed : 63 Total amount earned by Teams: Rs. 140430 | Total number of sanitising Teams: 8 Total work orders executed : 64 Total amount earned by Teams: Rs. 144980 | Total number of sanitising Teams: 8 Total work orders executed : 69 Total amount earned by Teams: Rs. 158060 | Total number of sanitising Teams: 8 Total work orders executed : 74 Total amount earned by Teams: Rs.177768
13 | Kannur | 60 | Progressing | Total number of sanitising Teams: 2 Total work orders executed : 6 Total amount earned by Teams: Rs. 15500 | Total number of sanitising Teams: 2 Total work orders executed : 9 Total amount earned by Teams: Rs. 16100 | Total number of sanitising Teams: 5 Total work orders executed : 25 Total amount earned by Teams: Rs. 47800 | Total number of sanitising Teams: 5 Total work orders executed : 43 Total amount earned by Teams: Rs. 85850 | Total number of sanitising Teams: 5 Total work orders executed : 52 Total amount earned by Teams: Rs. 97400 | Total number of sanitising Teams: 5 Total work orders executed : 67 Total amount earned by Teams: Rs. 121800 | Total number of sanitising Teams: 5 Total work orders executed : 78 Total amount earned by Teams: Rs. 137250 | Total number of sanitising Teams: 5 Total work orders executed : 86 Total amount earned by Teams: Rs. 152900 | Total number of sanitising Teams: 8 Total work orders executed : 89 Total amount earned by Teams: Rs. 163000 | Total number of sanitising Teams: 8 Total work orders executed : 93 Total amount earned by Teams: Rs. 167700
14 | Kasaragod | 70 | Progressing | Total number of sanitising Teams: 5 Total work orders executed : 9 Total amount earned by Teams: Rs. 9000 | Total number of sanitising Teams: 5 Total work orders executed : 22 Total amount earned by Teams: Rs. 17250 | Total number of sanitising Teams: 5 Total work orders executed : 56 Total amount earned by Teams: Rs. 64550 | Total number of sanitising Teams: 7 Total work orders executed : 60 Total amount earned by Teams: Rs. 70150 | Total number of sanitising Teams: 7 Total work orders executed : 122 Total amount earned by Teams: Rs. 110350 | Total number of sanitising Teams: 7 Total work orders executed :181 Total amount earned by Teams: Rs. 135300 | Total number of sanitising Teams: 7 Total work orders executed :212 Total amount earned by Teams: Rs. 164600 | Total number of sanitising Teams: 7 Total work orders executed :232 Total amount earned by Teams: Rs. 191950 | Total number of sanitising Teams: 8 Total work orders executed :256 Total amount earned by Teams: Rs. 202950 | ,
|  | 1000 |  |  | .