## Weekly Target and Achievement
PMAY (U) -LIFE
DISTRICT TARGET AND ACHIEVEMENT
NO | District | Before Commencement of 100 Days Programme |  | District wise Target for completion | Total to be completed before November 30 | Total Habitable as on 14. 09.2020 | Progress between 22.07.2020 & 14.09.2020 | Total Habitable as on 21.09.202 | Progress between 14.09.2020 & 21.09.2020 | Total Habitable as on 28.09.202 | Progress between 21.09.2020 & 28.09.2020 | Total Habitable as on 5.10.2020 | Progress between 28.09.2020 & 5.10.2020 | Total Habitable as on 12.10.2020 | Progress between 5.10.2020 & 12.10.2020 | Total Habitable as on 19.10.2020 | Progress between 12.10.2020 &19.10.2020
|  | 4th Installment released as on 22.07.2020 | Total Habitable (including Physically completed) as on 22.07.2020
| A | B | C | D | E = B+D | F | G = F-C | H | I = H-F | J | K = J-H | L | M = L-J | N | O = N-L | P | Q=P-N
1 | Alappuzha | 1889 | 2653 | 2020 | 3909 | 2653 | 0 | 2849 | 196 | 2875 | 26 | 2893 | 18 | 2925 | 32 | 2963 | 38
2 | Ernakulam | 5114 | 6074 | 2563 | 7677 | 6086 | 12 | 6495 | 409 | 6516 | 21 | 6539 | 23 | 6544 | 5 | 6589 | 45
3 | Idukki | 1268 | 1464 | 315 | 1583 | 1464 | 0 | 1500 | 36 | 1503 | 3 | 1505 | 2 | 1509 | 4 | 1515 | 6
4 | Kannur | 2613 | 3074 | 1185 | 3798 | 3074 | 0 | 3326 | 252 | 3385 | 59 | 3423 | 38 | 3464 | 41 | 3501 | 37
5 | Kasargod | 803 | 1091 | 440 | 1243 | 1091 | 0 | 1298 | 207 | 1308 | 10 | 1319 | 11 | 1331 | 12 | 1337 | 6
6 | Kollam | 3472 | 3863 | 1520 | 4992 | 4220 | 357 | 4240 | 20 | 4293 | 53 | 4352 | 59 | 4387 | 35 | 4434 | 47
7 | Kottayam | 1359 | 1544 | 593 | 1952 | 1544 | 0 | 1595 | 51 | 1651 | 56 | 1679 | 28 | 1679 | 0 | 1680 | 1
8 | Kozhikkode | 2798 | 3159 | 2459 | 5257 | 3213 | 54 | 3497 | 284 | 3517 | 20 | 3536 | 19 | 3554 | 18 | 3605 | 51
9 | Malappuram | 3755 | 5373 | 4587 | 8342 | 5575 | 202 | 5825 | 250 | 6103 | 278 | 6141 | 38 | 6169 | 28 | 6207 | 38
10 | Palakkad | 2519 | 3645 | 2721 | 5240 | 3745 | 100 | 3785 | 40 | 3830 | 45 | 3844 | 14 | 3882 | 38 | 3974 | 92
11 | Pathanamthitta | 802 | 980 | 439 | 1241 | 980 | 0 | 999 | 19 | 1028 | 29 | 1045 | 17 | 1056 | 11 | 1137 | 81
12 | Thiruvananthapuram | 5943 | 8696 | 3390 | 9333 | 8696 | 0 | 9124 | 428 | 9312 | 188 | 9353 | 41 | 9387 | 34 | 9524 | 137
13 | Thrissur | 3537 | 4994 | 2207 | 5744 | 4994 | 0 | 5273 | 279 | 5325 | 52 | 5341 | 16 | 5383 | 42 | 5393 | 10
14 | Wayanad | 1207 | 1835 | 1089 | 2296 | 1835 | 0 | 1847 | 12 | 1849 | 2 | 1852 | 3 | 1861 | 9 | 1946 | 85
| Total | 37079 | 48445 | 25528 | 62607 | 49170 | 725 | 51713 | 2543 | 52495 | 782 | 52822 | 327 | 53131 | 309 | 53805 | 674

## Sheet2
100 DAYS PRORAMME
PMAY (U)-LIFE HABITABLE HOUSES
NO | District | Total Habitable as on 21.09.202
1 | Alappuzha | 2849
2 | Ernakulam | 6495
3 | Idukki | 1500
4 | Kannur | 3326
5 | Kasargod | 1298
6 | Kollam | 4240
7 | Kottayam | 1595
8 | Kozhikkode | 3497
9 | Malappuram | 5825
10 | Palakkad | 3785
11 | Pathanamthitta | 999
12 | Thiruvananthapuram | 9024
13 | Thrissur | 5273
14 | Wayanad | 1847
| Total | 51713